City University of Hong Kong

Department of Electrical Engineering  ·  Final Year Project EE4080  ·  2026/27 A

Project Summary and Planning Chart

MIFlu-Based Comparison of Non-LLM and LLM Influenza Forecasting Architectures with Independent Test/Holdout Generalization Evaluation

1.  Student and Project Information

| Field | Value | Field | Value |
| --- | --- | --- | --- |
| Student No. | 58324980 | Student Name | CHAN Sing Yeung |
| CityU Email | sychan552-c@my.cityu.edu.hk | Project Code | KHC-04 |
| Course | EE4080 | Project Supervisor | KHC — Prof CHAN, Katie |
| Programme | Bachelor of Engineering (BENGEGU4) | Programme-Major | Bachelor of Engineering — Computer and Data Engineering |
| Home Major | Computer and Data Engineering (CDE) | Department | Electrical Engineering (EE) |
| College | College of Engineering (EG) | Level / Mode | Bachelor's Degree / Full-time |
| Expected Date of Graduation | 1 June 2027 | Remark / Project Category | Software |
| Academic Year / Term | 2026/27 A | Project Assessor | [NOT YET SHOWN / TO BE ASSIGNED] |

Project category: a software and methodological study. All quantitative statements in this chart are drawn from the current MIFlu evidence pack and are reported separately for the Wave-1 validation phase and the one-time Test/Holdout phase.

2.  Project Summary / Abstract

This project is a reproducible, leakage-controlled and independently audited comparison of lightweight Non-LLM and LLM-based architectures for multivariate influenza-like-illness (ILI) forecasting, followed by an isolated Test/Holdout generalization evaluation. All models share one dataset and chronological split, one seven-variable input/output contract, one train-only scaler, four forecast horizons L in {24, 36, 48, 60} weeks, ten frozen seeds (42-51), deterministic baselines, ablations and negative controls.

Wave-1 compared four Non-LLM architectures (NLinear, DLinear, a PatchTST-inspired implementation, iTransformer) with four LLM-based architectures (GPT-2 MIFlu, Qwen Time-LLM, CALF, TimeCMA), together with two deterministic references, six ablations and negative controls. Wave-1 produced 580 accepted experimental rows (320 primary-model, 8 baseline, 240 ablation, 12 negative-control) with zero reported ledger failures, deletions or duplicated accepted rows. Under the frozen selection rule - average_MSE_4L in seven-variable, full-horizon z-space, lower better - GPT-2 MIFlu was the Wave-1 validation winner (0.771; paired t = -13.33, p = 3.13e-07 against the runner-up) and NLinear was the best Non-LLM model and overall runner-up (1.070). At family level the Non-LLM group (1.142) was more accurate than the LLM group (1.243), p = 1.44e-06.

After a pre-Test freeze audit, the authorised final comparison set - GPT-2 MIFlu, NLinear and the deterministic Seasonal-Naive reference - was evaluated exactly once on the isolated Test/Holdout window (target absolute weeks 820-1024, a contiguous COVID-era period). All 84 runs completed and the terminal audit passed 25/25. Within that frozen Test comparison set, NLinear obtained the lowest average_MSE_4L (2.739) ahead of GPT-2 MIFlu (3.051) and Seasonal-Naive (4.279); the GPT-2-minus-NLinear difference (+0.312) is significant after Holm-Bonferroni correction (p = 4.0e-04), and both learned models outperformed Seasonal-Naive (p < 1e-08).

Because only the frozen three-model set was released Test access, this does not establish that NLinear defeats all eight architectures on Test, and it does not support a universal claim that LLM-based forecasting is inferior. The Test window is one contiguous distribution-shifted holdout in which COVID effects and distribution shift cannot be separated. Project success is defined as delivering a valid, fair, auditable and reproducible comparison with frozen selection and documented integrity evidence - not as demonstrating in advance that either model family must win.

3.  Design Problem and Motivation

The design problem is a comparison-and-evaluation problem rather than a pure accuracy-maximisation problem: does any apparent advantage of LLM-based forecasting survive a fair protocol and an independent, distribution-shifted holdout?

• Operational value of influenza forecasting. Weekly ILI forecasts support preparedness and capacity planning. Their value depends on remaining useful outside the training regime, so robustness matters as much as in-sample accuracy.

• Why the Non-LLM vs LLM comparison matters technically. LLM-based forecasters add a frozen language backbone, textual prompts and cross-modal alignment, with large parameter, memory and runtime costs. Their benefit must be demonstrated against simple linear and attention-based baselines, not assumed.

• Why validation scores alone are insufficient. A validation split can reward a model that has memorised the seasonal shape of the training era. In this dataset the zero-parameter Seasonal-Naive reference was competitive with the LLM champion on validation at L = 24, 36 and 48.

• Why the protocol must be harmonised. Differences in split, scaling, output variables, horizon, seeds or checkpoint selection can masquerade as architectural differences; deterministic baselines and negative controls are needed to bound optimism.

• Why an isolated Test/Holdout is needed. Only a window used for no fitting, no early stopping and no model selection can measure generalization under temporal distribution shift; here it was accessed once, under a frozen script and audited workflow.

• Why efficiency and reproducibility matter alongside accuracy. A technique that is orders of magnitude more expensive must justify its cost, so parameter count, training time, checkpoint size and restoration checks are reported next to accuracy.

Claim boundary: this project evaluates forecasting architectures and research methodology. It does not claim to deliver, validate or deploy a clinical or public-health decision system.

4.  Aim and Measurable Objectives

Aim. To determine, by a pre-registered, seed-replicated and audit-controlled experiment, whether LLM-based influenza forecasting architectures retain an accuracy advantage over lightweight Non-LLM architectures once the comparison is made fair and is then tested on an isolated, distribution-shifted Test/Holdout window.

Table 4-1  Objectives paired with verification method, deliverable and status

| ID | Objective (measurable) | Verification method / deliverable | Status |
| --- | --- | --- | --- |
| O1 | Reproduce and verify the MIFlu seven-variable long-horizon protocol without leakage: T = 104-week input, L in {24, 36, 48, 60}, train-only StandardScaler, chronological split, no shuffling. | Documented protocol read-through plus leakage/isolation audit with zero tolerated findings, verified before any Test access. | Completed |
| O2 | Compare four Non-LLM and four LLM-based architectures under identical splits, preprocessing, horizons, seeds (42-51) and metric definitions. | 320 primary rows in the frozen experiment matrix with per-horizon and per-seed MSE/MAE tables. | Completed - 320/320 primary rows accepted |
| O3 | Evaluate complete-output (seven-variable, full-horizon) MSE/MAE plus supplementary ILITOTAL fixed-step, full-horizon and formally defined PTE/PIE analyses. | Four metric families per row; average_MSE_4L and average_MAE_4L summaries; secondary ILITOTAL and PTE/PIE tables. | Completed |
| O4 | Use two deterministic baselines, six ablations and negative controls to examine whether textual prompting, LoRA and multimodal mechanisms add evidence-supported value. | Baseline comparison table; six matched-seed ablation contrasts with p-values; documented negative controls with conclusions matched to statistical strength. | Substantially completed - executed controls plus six newly executed deferred controls bound to their lawful parent model |
| O5 | Freeze validation-based selection, then run an audited one-time Test/Holdout comparison of the authorised final comparison set only (GPT-2 MIFlu, NLinear, Seasonal-Naive). | Pre-Test freeze audit green (test_access = 0, holdout_access = 0), 84/84 runs, terminal audit 25/25, frozen script hash unchanged. | Completed - executed exactly once |
| O6 | Compare accuracy, stability, computational cost and resource use; produce auditable artifacts, figures, report, presentation and demonstration. | Seed SD and 95% CI; per-model training time, trainable parameters and compact checkpoint size; reproducibility archive and figure/table provenance. | Cost analysis and report drafts completed; presentation, demonstration, Final Report and archive still planned |

Scope note: objectives O1-O4 apply to the eight-architecture Wave-1 validation benchmark; objective O5 applies only to the three-model frozen Test/Holdout comparison set.

5.  Scope, Boundaries and Deliverables

5.1  In scope

• National weekly multivariate ILI series (1,025 weekly time points, seven variables) treated as a multivariate long-horizon forecasting task.

• Eight primary architectures - four Non-LLM and four LLM-based - harmonised to one interface.

• Four horizons L in {24, 36, 48, 60} weeks and ten frozen seeds for stochastic models.

• Two deterministic references, six ablations of the GPT-2 MIFlu configuration, executed negative controls and six newly executed deferred controls.

• One-time Test/Holdout evaluation restricted to the frozen three-model comparison set.

• Accuracy, stability, cost, artifact-integrity and reproducibility analysis.

5.2  Explicitly out of scope

• Test/Holdout evaluation of all eight architectures - only three frozen models were authorised.

• A second, non-COVID-era holdout; distribution shift and COVID effects cannot therefore be separated.

• Deployment as a clinical, epidemiological or public-health decision system.

• Regional (multi-location) ILI experiments beyond the national task used here.

• Any hyper-parameter search on Test/Holdout, and any post-hoc mutation of the frozen selection rule.

Figure 5-1  System scope and evidence-flow block diagram. Each block produces the evidence listed on the right before the next block may start; the freeze gate (D6) is the only point at which Test/Holdout data become accessible.

| System block | Evidence produced |
| --- | --- |
| D1 Data and split governance National weekly ILI series: 1,025 weekly points, 7 variables; chronological split (train / validation / Test-Holdout, validation ends at week 819); StandardScaler fitted on the training split only | Dataset identity check; leakage and isolation audit |
| ▼ |  |
| D2 Common input / output contract Input: past T = 104 weeks x 7 variables; output: all 7 variables over L in {24, 36, 48, 60}; frozen seeds 42-51 for stochastic models | Frozen experiment matrix |
| ▼ |  |
| D3 Model pool Four Non-LLM (NLinear, DLinear, PatchTST-inspired, iTransformer) plus four LLM-based (GPT-2 MIFlu, Qwen Time-LLM, CALF, TimeCMA), two deterministic references, six ablations and controls | Harmonised interfaces; per-row metric files |
| ▼ |  |
| D4 Execution All heavy computation submitted with sbatch to the stingy partition; pre-execution Gate verifies the checkpoint save / restore round trip; serial fail-stop controller | Job ledger; row manifests; Gate evidence |
| ▼ |  |
| D5 Wave-1 validation (580 accepted rows) Four metric families per row; ranking by average_MSE_4L with forbidden tie-breakers; no post-hoc change to the selection rule | Selection outcome (validation only) |
| ▼ |  |
| D6 Freeze gate Pre-Test freeze audit: test_access = 0 and holdout_access = 0 before release; frozen script hash | Freeze audit record; one-time access ledger |
| ▼ |  |
| D7 Test / Holdout evaluation (one-time) Frozen three-model comparison set only - GPT-2 MIFlu, NLinear, Seasonal-Naive; 84 runs; validation-selected checkpoints and train-fitted scaling reused | 84 run manifests; terminal audit 25/25 |
| ▼ |  |
| D8 Interpretation and outputs Secondary ILITOTAL and PTE / PIE analysis, cost and resource comparison, figures and tables with provenance, then report, presentation, demonstration and archive | Final Report; reproducibility package |
| Boundary (out of scope): evaluation of all eight architectures on Test/Holdout, a second non-COVID-era holdout, clinical or public-health deployment, regional ILI experiments, and any hyper-parameter search on Test/Holdout. |  |

5.3  Deliverables

Table 5-1  Deliverables and status

| ID | Deliverable | Status |
| --- | --- | --- |
| D1 | Verified seven-variable MIFlu reproduction pipeline with leakage audit | Completed |
| D2 | Eight-architecture Wave-1 benchmark (320 primary rows) with per-horizon/per-seed metrics | Completed |
| D3 | Deterministic baselines, six ablations and documented controls | Completed |
| D4 | Frozen selection rule and statistical aggregation with confidence intervals and paired tests | Completed |
| D5 | One-time Test/Holdout evidence pack: 84 runs, freeze audit, terminal audit 25/25 | Completed |
| D6 | Supplementary ILITOTAL fixed-step / full-horizon and formally defined PTE/PIE analysis | Completed |
| D7 | Computational-cost and resource comparison; editable tables and figures with provenance | Completed |
| D8 | This Project Summary and Planning Chart | Finalised for student verification |
| D9 | Progress Report and progress presentation to supervisor and assessor | Planned - due 20 November 2026 |
| D10 | Final Report, final presentation, demonstration and reproducibility archive | Planned - Semester B, Weeks 10-12 |

6.  Background and Related Work

MIFlu (Moon, Shim, Kim and Hwang, IEEE Journal of Biomedical and Health Informatics, 2025) proposes a multimodal influenza forecasting scheme in which textual domain knowledge is embedded by one language model and fused with patched multivariate time-series embeddings before being passed to a forecasting language model fine-tuned with low-rank adaptation. That claim motivates this project, but the paper releases neither code nor the exact optimisation schedule, so the implementation used here is an independent re-implementation whose absolute error levels were never expected to match the publication.

Parallel work questions how much of such a gain is attributable to the language machinery. Lightweight linear baselines have been shown to match or beat complex transformers on long-horizon benchmarks; patch-based and inverted-attention transformers provide strong non-textual alternatives; and reprogramming or cross-modal alignment approaches adapt frozen language models to time series without an explicit textual channel. Because these families also differ in normalisation, output contract, horizon and tuning practice, a third-party comparison under one protocol is needed before any ordering can be believed.

Two further strands shape the method. First, evaluation-integrity work on time-series benchmarks shows that unfair scaling, reused validation budgets and post-hoc selection can create spurious advantages - hence the freeze, audit and one-time access discipline. Second, operational ILI evaluation traditionally uses peak-timing and peak-intensity criteria in addition to point-wise error, which motivates retaining formally defined peak metrics as secondary analyses. Bibliographic metadata for the implemented comparators is listed in Section 16; entries marked for verification are not yet confirmed against a library record.

7.  Methodology and System Workflow

The workflow is staged so that every phase has an explicit exit artefact and so that no phase reading held-out targets can begin before its gate is green. Figure 7-1 shows the stage sequence, which implements the eighteen protocol steps of the study.

Figure 7-1  Staged system workflow (each stage flows into the next; every stage has an exit gate)

| Stage | Key activities | Exit artefact / gate |
| --- | --- | --- |
| S1 | Literature review and MIFlu protocol verification; dataset identity and chronological split checks; train-only scaling and contamination/leakage audit; common seven-variable input/output contract. | Documented protocol decisions; leakage/isolation audit with zero findings |
| S2 | Implementation and harmonisation of the eight primary architectures plus two deterministic references, six ablations and negative controls on one shared interface. | Immutable experiment matrix: run keys, seeds, horizons, variants |
| S3 | Reproducible batch execution system, weight discipline and pre-execution Gate validation (checkpoint save/restore round trip verified before any row runs). | Gate evidence; deterministic rows declared checkpoint-inapplicable |
| S4 | Formal Wave-1 validation execution across all rows: serial fail-stop control, one immutable checkpoint path per row. | Row-level metrics in four metric families; ledger events |
| S5 | Completion, artifact, metadata, checkpoint and durable-copy audit; bit-exact compact checkpoint extraction. | Completeness reconciliation: 580/580 Wave-1 rows, 0 deleted, 0 duplicated |
| S6 | Statistical aggregation over frozen seeds and frozen architecture selection under the pre-registered rule; no post-hoc tie-breaking. | Selection outcome with paired statistics and equivalence reporting |
| S7 | Deferred-control parent binding and, where authorised, focused control execution against the correct parent model. | Six executed rows bound to their lawful parent; matched-parent contrasts only |
| S8 | Pre-Test freeze audit and authorisation; Test/Holdout stays sealed (test_access = 0, holdout_access = 0) until release. | Freeze audit green; access ledger opened only on release |
| S9 | One-time Test/Holdout execution for the frozen three-model comparison set under the frozen script, then terminal audit and generalization analysis. | 84/84 runs; terminal audit 25/25; script hash unchanged |
| S10 | Supplementary formal ILITOTAL/PTE-PIE analysis, computational and resource comparison, figure and table generation with source provenance. | Editable figures/tables with per-figure provenance records |
| S11 | Reporting, presentation, demonstration, final artifact QA and reproducibility archive. | Final Report, presentation, demonstration; archived reproducible bundle |

7.1  Compute environment and execution discipline

All substantial computation is executed through batch submission. Training, inference, evaluation and figure generation are submitted with sbatch to the stingy partition of the shared HPC facility, respecting that partition's concurrency and wall-clock limits; jobs are chained and polled rather than run interactively. The login node is used only for job submission, queue polling, small-file transfer and text inspection - no training, inference, evaluation or background computation is run there. This discipline also protects reproducibility, because every result-bearing run is produced by a scripted, logged batch job rather than by interactive session state.

7.2  Frozen experimental configuration

Table 7-1  Frozen experimental configuration

| Item | Setting |
| --- | --- |
| Dataset | National weekly multivariate ILI series; 1,025 weekly time points; seven variables |
| Input / output contract | Input: past T = 104 weeks, all seven variables. Output: all seven variables over the full horizon |
| Horizons | L = 24, 36, 48, 60 weeks |
| Scaling | StandardScaler fitted on the training split only; validation and Test are transformed only |
| Split | Chronological, no shuffling; validation ends at absolute week 819; Test targets 820-1024 |
| Seeds | 42-51 (ten frozen seeds) for stochastic models; deterministic references have no seed |
| Primary metric | mse_all_7vars_full_horizon_z, aggregated over horizons as average_MSE_4L |
| Secondary metrics | average_MAE_4L; ILITOTAL fixed-step and full-horizon; PTE/PIE (secondary only) |
| Selection rule (frozen) | Rank by average_MSE_4L; then average_MAE_4L; then declared resource cost. Forbidden: peak-hit ratio, PTE/PIE, baseline-relative ratio, (r24+r60)/2 |
| Early stopping / checkpoint | Validation-based selection with fixed patience; the validation-selected checkpoint is reused at Test time |

8.  Evaluation and Statistical Analysis Plan

Primary endpoint. Accuracy is measured by complete seven-variable, complete-horizon MSE in train-only z-space, aggregated first over the ten seeds within a horizon and then over the four horizons to give average_MSE_4L. average_MAE_4L is the key secondary endpoint. Point estimates are seed means; 95% confidence intervals are t-intervals over ten seeds (df = 9).

Confirmatory tests. Three tests were pre-registered on average_MSE_4L for the Test/Holdout phase and corrected with Holm-Bonferroni step-down at family size m = 3, alpha = 0.05: C1 (GPT-2 MIFlu vs NLinear, matched-seed paired t, n = 10 pairs), C2 (GPT-2 MIFlu vs Seasonal-Naive) and C3 (NLinear vs Seasonal-Naive). The latter two are one-sample tests of per-seed differences against a deterministic reference that contributes no seed variance. Effect sizes (Cohen's dz) are reported with each test.

Secondary analyses. ILITOTAL fixed-step and full-horizon analyses are computed in the physical (inverse-transformed) scale. Peak-timing error (PTE) and peak-intensity error (PIE) use convention thresholds of 1 week and 25% and are reported per horizon over eligible season/lead combinations. PTE and PIE are application-facing secondary metrics: they never enter model selection, and aggregate figures must not replace the formal per-season definition with representative lead-1 curve summaries.

Integrity controls. Model selection uses validation only. Test/Holdout targets are read only through the frozen evaluation script after the pre-Test freeze audit; the phase runs once; script hash, access ledger, per-row artifacts, checkpoint-restoration evidence and terminal audit counts are retained as evidence. Non-significant findings are reported as non-significant; they are never presented as proof of zero effect.

9.  Current Status and Verified Evidence

Table 9-1  Status classification - completed, in progress, planned and contingency work are reported separately

| Status | Item | Evidence |
| --- | --- | --- |
| Completed | MIFlu protocol verification; dataset/split/scaler checks; leakage and isolation controls | Leakage and manifest evidence in the Wave-1 artifact set |
| Completed | Eight harmonised architectures, two deterministic references, six ablations, executed negative controls | Frozen experiment matrix and row-level metric artifacts |
| Completed | Wave-1 validation execution and post-row audit - 580/580 accepted rows; 0 deleted; 0 duplicated | Row manifests, completeness reconciliation, durable evidence copies |
| Completed | Frozen selection and statistical aggregation (10 seeds x 4 horizons) | Selection outcome with paired tests and confidence intervals |
| Completed | Deferred-control resolution: 12 controls matched to existing accepted rows; 6 controls newly executed against their lawful parent model | Amendment record and control effect tables |
| Completed | Pre-Test freeze audit and one-time Test/Holdout execution for the frozen three-model set (84/84 runs, terminal audit 25/25) | Freeze audit, access ledger, terminal audit |
| Completed | Supplementary ILITOTAL and PTE/PIE analyses; cost/resource comparison; figures and tables with provenance | Metric tables, cost table, figure manifest |
| In progress / under review | This Planning Chart (finalisation and administrative verification) | This document |
| Planned | Supervisor review cycles; Progress Report and presentation; Final Report; final presentation; demonstration; reproducibility archive | Course deliverables - see Section 13 |
| Contingency / optional | Further control expansion beyond the authorised set; any additional holdout | Only if the supervisor authorises an amendment; not assumed |

10.  Key Results to Date

10.1  Wave-1 validation findings (validation split only - not Test)

Table 10-1  Wave-1 validation ranking by average_MSE_4L (lower is better); ten seeds per model. Training time and trainable parameters are mean values from the cost audit.

| Rank | Model | Family | average MSE 4L | 95% CI | average MAE 4L | Training time (s) | Trainable parameters |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | gpt2_miflu | LLM | 0.771 | [0.720, 0.822] | 0.487 | 147.3 | 1,030,056 |
| 2 | nlinear | Non-LLM | 1.070 | [1.068, 1.072] | 0.564 | 5.3 | 2,520 |
| 3 | patchtst (PatchTST-inspired) | Non-LLM | 1.076 | [1.065, 1.087] | 0.556 | 8.4 | 87,256 |
| 4 | dlinear | Non-LLM | 1.171 | [1.168, 1.174] | 0.603 | 5.7 | 5,040 |
| 5 | timecma_llm | LLM | 1.181 | [1.170, 1.193] | 0.614 | 15.2 | 1,391,016 |
| 6 | itransformer | Non-LLM | 1.253 | [1.248, 1.258] | 0.598 | 8.5 | 75,672 |
| 7 | qwen_time_llm | LLM | 1.253 | [1.223, 1.283] | 0.649 | 338.7 | 370,376 |
| 8 | calf_llm | LLM | 1.765 | [1.756, 1.774] | 0.773 | 20.2 | 1,981,608 |

• Winner vs runner-up (validation): GPT-2 MIFlu 0.771 vs NLinear 1.070; mean difference -0.299, paired t = -13.33, p = 3.13e-07, Cohen's dz = -5.94, n = 10 seed pairs.

• Family comparison (validation): Non-LLM group mean 1.142 vs LLM group mean 1.243; paired t = -11.15, p = 1.44e-06. The family result is carried by a single model and is reported separately from the single-model winner.

• Deterministic reference (validation): Seasonal-Naive MSE 0.719 / 0.732 / 0.746 / 0.885 at L = 24 / 36 / 48 / 60, i.e. competitive with the LLM champion at L = 24, 36 and 48. Last-value naive was far worse (2.82-3.42).

• Supplementary ILITOTAL z-space (validation): GPT-2 MIFlu best (1.608), then NLinear (2.333), DLinear (2.526) and PatchTST-inspired (2.544).

• Stability: on average_MSE_4L the seed SD is 0.003 for NLinear and 0.071 for GPT-2 MIFlu - the smallest and largest dispersion in the field respectively.

10.2  Independent Test/Holdout findings (frozen three-model comparison set only)

Only three models were evaluated on Test/Holdout: GPT-2 MIFlu, NLinear and the deterministic Seasonal-Naive reference. The other five architectures were NOT evaluated on Test/Holdout, and no Test ordering across all eight models is claimed.

Table 10-2  One-time Test/Holdout results on the primary endpoint average_MSE_4L (lower is better). Gap = Test minus validation average_MSE_4L.

| Model | Family / arm | Test MSE 4L | Test 95% CI | Test MAE 4L | Validation MSE 4L | Gap |
| --- | --- | --- | --- | --- | --- | --- |
| nlinear | Non-LLM | 2.739 | [2.731, 2.747] | 1.139 | 1.070 | +1.67 |
| gpt2_miflu | LLM | 3.051 | [2.922, 3.179] | 1.156 | 0.771 | +2.28 |
| seasonal_naive | Deterministic baseline | 4.279 | n/a (deterministic) | 1.299 | 0.771 | +3.51 |

Execution scale and audit: 84 runs completed (40 GPT-2 MIFlu, 40 NLinear, 4 Seasonal-Naive), all ledger entries COMPLETED with exit 0:0; no duplicate or unauthorised run; 84 result directories, manifests, prediction files and metric files; 80/80 stochastic rows passed strict checkpoint restoration; terminal audit 25/25; frozen script hash unchanged; Test targets at absolute weeks 820-1024.

Table 10-3  Test/Holdout per-horizon MSE (seed mean) with the matched-seed GPT-2-minus-NLinear contrast per horizon (paired t, n = 10)

| Horizon | gpt2_miflu | nlinear | seasonal_naive | Mean difference | Paired-test reading |
| --- | --- | --- | --- | --- | --- |
| L = 24 | 2.750 | 2.337 | 4.158 | +0.413 | p = 0.0039 (significant) |
| L = 36 | 3.182 | 2.705 | 4.277 | +0.477 | p = 0.0043 (significant) |
| L = 48 | 3.189 | 2.907 | 4.383 | +0.283 | p = 0.055 (marginal) |
| L = 60 | 3.081 | 3.007 | 4.299 | +0.074 | p = 0.175 (not significant) |

Table 10-4  Pre-registered confirmatory tests on average_MSE_4L with Holm-Bonferroni correction (m = 3, alpha = 0.05)

| Test | Hypothesis | Mean difference | t | Raw p | Holm p | Decision (alpha = 0.05) |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | gpt2_miflu worse than nlinear on Test | +0.312 | 5.461 | 4.0e-04 | 4.0e-04 | Reject H0 |
| C2 | gpt2_miflu better than seasonal_naive on Test | -1.229 | -21.614 | 4.6e-09 | 9.2e-09 | Reject H0 |
| C3 | nlinear better than seasonal_naive on Test | -1.540 | -443.368 | 7.7e-21 | 2.3e-20 | Reject H0 |

• Within the frozen Test comparison set, NLinear has the lowest average_MSE_4L and the confidence intervals of the two learned models do not overlap, so the reversal of the validation ordering is not a sampling artefact of this comparison.

• Both learned models outperform the zero-parameter Seasonal-Naive reference on this window, supporting a two-tier reading: learning helps, while the marginal value of the LLM machinery over a linear model is negative on this particular window.

• The ILITOTAL physical endpoint preserves the same ordering (NLinear 3.97e+08 MSE / 13,670 MAE; GPT-2 MIFlu 4.66e+08 / 14,313; Seasonal-Naive 6.60e+08 / 16,174), so the primary ranking is endpoint-robust.

• Peak metrics (Test, physical ILITOTAL, secondary): NLinear reaches PIE 9.2-21.1% with joint timing-plus-intensity hit rates up to 0.63; GPT-2 MIFlu 41.4-61.5%; Seasonal-Naive 49.6-123.9% despite good raw timing at long horizons. These are application metrics only and were never used for selection.

10.3  Ablation and control evidence (validation) - matched to statistical strength

Table 10-5  Six GPT-2 MIFlu ablations vs the unablated parent (parent average_MSE_4L = 0.771); matched-seed paired t-tests, n = 10 seeds

| Ablation | average MSE 4L | Delta vs parent | p | n | Interpretation matched to strength |
| --- | --- | --- | --- | --- | --- |
| without_dataset_information | 0.870 | +12.85% | 0.0036 | 10 | Significant; strongest single ablation effect |
| without_input_variable_description | 0.816 | +5.80% | 0.079 | 10 | Non-significant; directional only |
| without_task_instruction | 0.793 | +2.82% | 0.395 | 10 | Non-significant |
| without_multimodality | 0.786 | +1.95% | 0.474 | 10 | Non-significant |
| without_lora_and_multimodality | 0.778 | +0.90% | 0.766 | 10 | Non-significant |
| without_lora | 0.773 | +0.26% | 0.947 | 10 | Non-significant |

Reading: only the removal of dataset information produced a statistically significant degradation; prompt-component and adaptation-mechanism removals were small and non-significant, and must be described that way rather than as evidence of zero contribution.

Table 10-6  Negative and deferred control evidence

| Group | Control / comparison | n | Mean delta | p | Reading |
| --- | --- | --- | --- | --- | --- |
| Negative controls, executed (exploratory) | zero_text | 6 | -0.063 | p = 0.254 | Small negative mean difference; not significant; reported descriptively |
| Negative controls, executed (exploratory) | shuffled_text | 6 | +0.081 | p = 0.398 | Small positive mean difference; not significant; not evidence of a harmful mechanism |
| Deferred controls resolved by equivalence | 12 specifications satisfied by exactly duplicated rows | - | - | - | Matched and recorded; no new duplicated statistical observation created |
| Deferred controls, newly executed | LLM / text branch removed (L = 24) | 3 | +0.024 | p = 0.490 | Non-significant at short horizon; n = 3, low power |
| Deferred controls, newly executed | LLM / text branch removed (L = 60) | 3 | +0.094 | raw p = 0.0015 | Supports a long-horizon contribution; n = 3, supportive rather than conclusive |

Note: the six newly executed rows were bound to their lawful parent model (TimeCMA), not to the GPT-2 MIFlu champion, because the control definition only applies to architectures that contain that branch.

11.  Limitations and Interpretation Boundaries

• Only three models (GPT-2 MIFlu, NLinear, Seasonal-Naive) were evaluated on Test/Holdout. No Test ordering across all eight architectures is available or claimed.

• The Test/Holdout window is a single contiguous COVID-era period (target absolute weeks 820-1024). Distribution shift and pandemic disruption cannot be causally separated; robustness conclusions are limited to this window.

• There is no second independent holdout, so the validation-to-Test gap should not be read as a pure measure of over-fitting.

• The deterministic Seasonal-Naive reference has no seed variance. Tests against it are one-sample tests with large t-values by construction; only direction and significance should be read, not magnitude.

• Peak metrics (PTE/PIE) depend on the reconstructed target-week and lead conventions and are secondary application metrics; aggregate summaries must not be presented as the formal per-season definition.

• The PatchTST comparator is an inspired re-implementation without the original pre-training configuration and reversible normalisation, so it must always be labelled PatchTST-inspired.

• The MIFlu reference implementation is independent; the original paper releases neither code nor the exact optimisation schedule, so agreement in absolute error levels was never expected or claimed.

• Deferred-control and negative-control contrasts use small per-horizon samples (n = 3 for the newly executed rows) and are therefore low-power; they are reported as supportive or exploratory, not conclusive.

• Non-significant ablations are not evidence that a component contributes nothing; they only indicate that no effect was detected at this sample size.

• A poor Seasonal-Naive result on the Test window does not make the baseline useless in general; it shows that a seasonal repeat does not transfer through this COVID-era disruption.

12.  Risk Management

Likelihood (L) and impact (I) are recorded as L (low), M (medium) or H (high). Risks that have already materialised are labelled realized and managed, with the response stated without exaggeration.

Table 12-1  Risk register (likelihood, impact, mitigation, trigger, contingency, status)

| ID | Risk | L | I | Mitigation | Trigger / indicator | Contingency | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | HPC queue delay or long runtime blocking the row pipeline | M | H | Batch-only submission to the stingy partition within its concurrency and wall-clock limits; rows chained automatically and retried idempotently. | Queue wait per pending job; job end reason | Serial fail-stop controller resumes from the ledger after requeue; accepted rows are never re-run. | Active |
| R2 | Deterministic runtime or dependency version failure | M | M | Pinned environment per phase; baseline rows declared checkpoint-inapplicable instead of being forced into the weights path. | Import or version mismatch at job start | Rebuild from the pinned environment file; excluded arms handled through a declared exception path. | Realized and managed |
| R3 | LLM asset or cache unavailability | M | H | Local asset cache plus integrity check before submission; no network dependency inside batch jobs. | Missing or corrupted asset at load time | Restore from the archived asset store and re-run only the affected row. | Active |
| R4 | Storage or checkpoint pressure causing truncated artifacts | M | H | Immutable per-row checkpoint directories; bit-exact compact checkpoints; full checkpoints released only after verified durable publication. | Quota utilisation; per-job directory growth | Quota-aware cleanup of superseded scratch trees; staged purge only after a durable copy is verified. | Realized and managed |
| R5 | Data leakage or split contamination | L | H | Chronological splits with no shuffling; scaler fitted on training only; explicit leakage assertions; Test targets strictly after validation week 819. | Leakage-audit assertion failures | Halt the row, quarantine the split, re-derive windows and re-run affected rows. | Controls green; continuously monitored |
| R6 | Checkpoint-restoration failure (unrecoverable weights) | M | H | Pre-execution Gate verifies the save/restore round trip; strict-load key checks for every stochastic Test row. | Differing keys or checksum mismatch on restore | Row rejected before its metric is accepted; row re-run from the seeded configuration. | Realized and managed (80/80 Test restoration checks passed) |
| R7 | Non-comparable output contracts or metric definitions | M | H | One seven-variable input/output contract and one metric definition for every row; per-row metrics written in four families. | Missing or inconsistent metric keys in a row | Metrics reconciler fails closed and blocks aggregation until the row is fixed. | Controlled |
| R8 | Incomplete, duplicated or corrupted artifacts | M | M | Row-level manifests, completeness reconciliation and durable-copy verification with counted rows. | Count mismatch between expected and published artifacts | Re-synchronise from the durable copy; keep the original row key; never silently overwrite. | Controlled (580/580 and 84/84 reconciled) |
| R9 | No statistically unique winner under the frozen rule | M | M | Pre-registered rule with declared tie-break order and forbidden tie-breakers; equivalence sets reported instead of a manufactured champion. | Non-significant difference between the top two models | Report the equivalence set and discuss it; never invent a post-hoc discriminator. | Not realized in validation; monitored |
| R10 | Validation-to-Test ranking reversal or distribution shift | H | M | Selection frozen before Test release; Test accessed once; pre-specified confirmatory tests with multiplicity control. | Terminal-audit and confirmatory test outcomes | Report both phases separately with explicitly bounded claims; never merge them into one unlabelled leaderboard. | Realized and managed - reported in Sections 10-11 |
| R11 | Over-interpretation of ablations and negative controls | H | M | Every contrast reported with p-value, sample size and power caveat; non-significant results labelled as such. | Reviewer challenge; internal wording audit | Reword to no effect detected; add power caveats; avoid slogans not supported by the evidence. | Active |
| R12 | Scope overload from many controls and ablations | M | M | Controls deferred by protocol rather than dropped; later bound to their lawful parent models under a documented amendment. | Row-count growth versus remaining time | Close the authorised subset and record the remainder as out of scope for this submission. | Realized and managed |
| R13 | Outdated official title or administrative mismatch | M | M | Visible action note at the top of this document; the current research title is used consistently in every section. | InfoNet record differing from the research title | Ask the supervisor and the FYP administrator to reconcile the record; do not assume approval of a title change. | Open - student action required |
| R14 | Writing, review, presentation and demonstration schedule risk | M | H | Drafting starts well before each deadline; supervisor review slots reserved; presentation and demonstration prepared in parallel with the Final Report. | Slippage against the milestone dates in Section 13 | Use the built-in contingency buffer in December and late April; reduce optional scope first. | Active |

13.  Two-Semester Planning Chart (September 2026 - April 2027)

Table 13-1  Two-semester planning chart (Gantt), September 2026 - April 2027. Each month is split into an early half (a) and a late half (b).

Legend and dependency rules are given immediately below the chart.

| ID | Task / milestone | Status | Path | Sep 2026 |  | Nov 2026 |  | Jan 2027 |  | Mar 2027 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Sep-a | Sep-b | Oct-a | Oct-b | Nov-a | Nov-b | Dec-a | Dec-b | Jan-a | Jan-b | Feb-a | Feb-b | Mar-a | Mar-b | Apr-a | Apr-b |
| T01 | Scope / title correction and official-form alignment | Completed | Slack | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T02 | Literature review and MIFlu protocol audit | Completed | CP | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T03 | Data split, train-only scaling, contamination controls | Completed | CP | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T04 | Eight-architecture implementation and harmonisation | Completed | CP | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T05 | Baselines, six ablations, negative controls | Completed | CP | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T06 | HPC execution system and pre-execution Gate | Completed | CP |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T17 | Planning Chart preparation and submission | In progress | CP | I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M1 | MILESTONE: Planning Chart submission (25 Sep 2026) | Milestone | CP |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T07 | Wave-1 validation execution (580 accepted rows) | Completed | CP |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T08 | Completion, artifact and durable-copy audit | Completed | CP |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |
| T09 | Statistical aggregation and frozen selection | Completed | CP |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |
| T18 | Supervisor review / result discussion (recurring) | In progress | Slack |  |  | I |  |  | I |  |  | I |  |  | I |  |  | I |  |
| T10 | Deferred-control binding and execution | Completed | Slack |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |
| T11 | Pre-Test freeze audit and authorisation | Completed | CP |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |
| T12 | One-time Test/Holdout execution (84 runs) | Completed | CP |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |
| T13 | Terminal Test audit, generalization analysis | Completed | CP |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |
| T14 | Formal ILITOTAL and PTE / PIE analysis | Completed | Slack |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |
| T15 | Resource and efficiency comparison | Completed | Slack |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |
| T19 | Progress Report preparation | Planned | CP |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |
| M2 | MILESTONE: Progress Report + presentation (Sem A Wk 12) | Milestone | CP |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |
| T20 | Progress presentation to supervisor / assessor | Planned | CP |  |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |
| T16 | Figure and table generation | Completed | Slack |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |
| T21 | Iteration: re-run / re-audit cycles | Contingency | Slack |  |  |  |  |  |  |  | B |  |  |  |  | B |  |  |  |
| T27 | Contingency buffer | Contingency | Slack |  |  |  |  |  |  |  | B |  |  |  |  |  |  |  | B |
| T22 | Final Report drafting | Planned | CP |  |  |  |  |  |  |  |  | P |  |  |  |  |  |  |  |
| T23 | Final Report revision and sign-off | Planned | CP |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |
| T24 | Final presentation preparation | Planned | Slack |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |  |
| T25 | Demonstration preparation and dry run | Planned | Slack |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |
| T26 | Final artifact QA and archive package | Planned | Slack |  |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |
| T28 | Abstract upload + plagiarism briefing (Sem B Wk 8) | Planned | Slack |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |
| M3 | MILESTONE: Final presentation (Sem B, Wk 10-12) | Milestone | CP |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M | M |
| M4 | MILESTONE: Demonstration (Sem B, Weeks 11-12) | Milestone | CP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M |
| M5 | MILESTONE: Final Report submission (Sem B, Wk 12) | Milestone | CP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M |
| T29 | FYP Competition poster (optional, Sem B Wk 13) | Contingency | Slack |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | B |

| D = Completed | I = In progress | P = Planned | B = Contingency / buffer | M = Milestone | CP = Critical path |
| --- | --- | --- | --- | --- | --- |

Chart notation: the letter in the first cell of each bar repeats the status shown in the Status column (D = completed, I = in progress, P = planned, B = contingency, M = milestone), so status is never conveyed by colour alone. The Path column marks critical path (CP) versus slack. Each month is divided into an early half (a) and a late half (b).

Dependency rules enforced by the chart:

• T03 (split, scaling and leakage controls) precedes T04-T06; the pre-execution Gate T06 precedes any Wave-1 row execution (T07).

• T07 precedes T08 (completion and artifact audit), which precedes T09 (statistical aggregation and frozen selection).

• T11 (pre-Test freeze audit) precedes T12 (one-time Test/Holdout execution), which precedes T13 (terminal audit and generalization analysis). No Test/Holdout work is scheduled before frozen selection and the freeze audit - this is a hard design constraint of the study.

• T13 and T16 (verified figures and tables) precede T22 (Final Report drafting); T23 (revision and supervisor sign-off) precedes M5 (Final Report submission).

• T24 (final presentation) and T25 (demonstration) begin before the Final Report deadline and run in parallel with T22 and T23, so presentation and demonstration work is not scheduled after submission.

• T21 (iteration) and T27 (buffer) absorb re-run or re-audit demand without moving the fixed school milestones M1-M5.

Table 13-2  Official FYP working schedule for students starting in Semester A 2026/27 (Department briefing: EE4080 FYP Briefing Session, Sem A 2026/27). Semester A dates are confirmed; Semester B entries are tentative and their exact calendar dates will be announced before Semester B begins.

| Term / week | Official action | Deadline or window | Status of date |
| --- | --- | --- | --- |
| Sem A Wk 4 | Upload Project Summary and Planning Chart onto FYP InfoNet | On or before 25 Sep 2026, 11:59 pm | Confirmed |
| Sem A Wk 12 | Upload Progress Report and present progress to supervisor and assessor | 16-20 Nov 2026; upload on or before 20 Nov 2026, 11:59 pm | Confirmed |
| Sem A Wk 12 | Confirm project title on FYP InfoNet (if necessary) | 16-20 Nov 2026 | Confirmed |
| Sem B Wk 7 | Finalize project title on FYP InfoNet | Tentative | Exact dates TBC |
| Sem B Wk 8 | Upload project abstract; announcement of presentation, demonstration and report submission details | Tentative | Exact dates TBC |
| Sem B Wk 8 | Briefing session on plagiarism check | Exact date to be confirmed | Exact dates TBC |
| Sem B Wk 10-12 | Project presentation (essential assessment element) | Tentative | Exact dates TBC |
| Sem B Wk 11-12 | Project demonstration with supervisor and assessor; submission of FYP report (soft copy, PDF, via Canvas) | Demonstration on or before Week 12 | Exact dates TBC |
| Sem B Wk 13 | Poster submission for FYP Competition (selected students only) | TBC | Optional |

14.  Work Packages, Dependencies, Milestones and Success Criteria

Table 14-1  Work package register - status, timing, predecessor, deliverable

| ID | Work package | Status | Timing | Predecessor | Deliverable / evidence |
| --- | --- | --- | --- | --- | --- |
| W01 | Scope / title correction and official-form alignment | Completed | Sep 2026 (Wk 1-4) | - | Corrected title block and administrative action note |
| W02 | Literature review and MIFlu protocol audit | Completed | Sep 2026 | W01 | Protocol read-through notes; reference list |
| W03 | Data split, train-only scaling and contamination controls | Completed | Sep 2026 | W02 | Leakage / isolation audit report |
| W04 | Eight-architecture implementation and harmonisation | Completed | Sep - Oct 2026 | W03 | Harmonised model interfaces |
| W05 | Baselines, six ablations and negative controls | Completed | Sep - Oct 2026 | W04 | Baseline and control rows |
| W06 | Reproducible HPC execution system and pre-execution Gate | Completed | Late Sep 2026 | W04, W05 | Batch scripts, ledgers, Gate evidence |
| W07 | Wave-1 validation execution (580 accepted rows) | Completed | Oct 2026 | W06 | Row-level metrics in four metric families |
| W08 | Completion, artifact, metadata and durable-copy audit | Completed | Oct 2026 | W07 | Completeness reconciliation and durable copies |
| W09 | Statistical aggregation and frozen selection | Completed | Oct 2026 | W08 | Selection outcome with paired tests |
| W10 | Deferred-control parent binding and execution | Completed | Oct - Nov 2026 | W09 | Amendment record; six executed rows |
| W11 | Pre-Test freeze audit and authorisation | Completed | Nov 2026 | W09, W10 | Freeze audit record (test_access = 0, holdout_access = 0) |
| W12 | One-time Test/Holdout execution (84 runs) | Completed | Nov 2026 | W11 | 84 run manifests and prediction files |
| W13 | Test/Holdout terminal audit and generalization analysis | Completed | Nov 2026 | W12 | Terminal audit 25/25; generalization comparison table |
| W14 | Formal ILITOTAL and PTE / PIE analysis | Completed | Nov - Dec 2026 | W12 | Secondary metric tables |
| W15 | Resource and efficiency comparison | Completed | Nov - Dec 2026 | W07 | Cost / storage table |
| W16 | Figure and table generation with provenance | Completed | Dec 2026 | W13, W14, W15 | Figure manifest and source data |
| W17 | Project Summary and Planning Chart | In progress | Sep 2026 (Sem A Wk 4) | W01-W16 | This document |
| W18 | Supervisor review and method / result discussion (recurring) | In progress | Monthly, Oct 2026 - Apr 2027 | W09 onward | Review notes and agreed revisions |
| W19 | Progress Report preparation | Planned | Oct - Nov 2026 (Sem A Wk 12: 16-20 Nov) | W13 | Progress Report draft |
| W20 | Progress presentation to supervisor and assessor | Planned | Nov 2026 (Sem A Wk 12: 16-20 Nov) | W19 | Slide deck and rehearsal notes |
| W21 | Iteration - re-run / re-audit cycles (reserved capacity) | Contingency | Dec 2026 and Mar 2027 | Triggered by W08 / W13 findings | Re-run rows and updated audits |
| W22 | Final Report drafting | Planned | Jan - Mar 2027 (Sem B Wk 1-8) | W13, W16 | Final Report draft |
| W23 | Final Report revision and supervisor sign-off | Planned | Mar - Apr 2027 (Sem B Wk 9-12) | W22 | Revised Final Report |
| W24 | Final presentation preparation | Planned | Feb - Apr 2027 (Sem B Wk 6-12) | W13, W16 | Slide deck and script |
| W25 | Demonstration preparation and dry run | Planned | Mar - Apr 2027 (Sem B Wk 8-12) | W16, W22 | Demonstration script and dry-run record |
| W26 | Final artifact QA, archive and reproducibility package | Planned | Mar - Apr 2027 (Sem B Wk 9-12) | W22, W23 | Archived bundle with manifests |
| W27 | Contingency buffer | Contingency | Dec 2026 and Apr 2027 | - | Reserved capacity |
| W28 | Upload project abstract onto FYP InfoNet | Planned | Sem B Wk 8 (2027) | W22 | Abstract uploaded to FYP InfoNet |
| W29 | Poster for FYP Competition (selected students only) | Contingency | Sem B Wk 13 (2027) | W22, W23 | Poster file if the student is selected |

Table 14-2  Success criteria, risk and mitigation, and critical-path classification (same IDs as Table 14-1)

| ID | Success criterion | Risk / mitigation | Critical path / slack |
| --- | --- | --- | --- |
| W01 | Document consistent with the current MIFlu direction | Admin record mismatch (R13) | Slack |
| W02 | Protocol elements identified and verified against the source paper | Gaps in the published protocol | CP |
| W03 | Zero leakage findings; scaler fit boundary proven | Leakage (R5) | CP |
| W04 | Identical input/output contract for all eight models | Non-comparable contracts (R7) | CP |
| W05 | Two deterministic references plus documented control definitions | Scope overload (R12) | CP |
| W06 | Every result-bearing run produced by a scripted batch job; restore round trip verified | Queue delay (R1), runtime failure (R2) | CP |
| W07 | 580/580 accepted; 0 deleted; 0 duplicated | Artifact corruption (R8) | CP |
| W08 | Counts reconcile; no row left unverified | Storage pressure (R4) | CP |
| W09 | Winner declared under the frozen rule; equivalence set reported if needed | No unique winner (R9) | CP |
| W10 | Controls bound to lawful parent models only | Over-interpretation (R11) | Slack |
| W11 | All gates green before release | Premature release (R5) | CP |
| W12 | 84/84 completed; frozen script hash unchanged | Restoration failure (R6) | CP |
| W13 | Validation and Test results reported separately with bounded claims | Ranking reversal (R10) | CP |
| W14 | Formal per-season definitions preserved; secondary status maintained | Convention dependence | Slack |
| W15 | Parameters, runtime and checkpoint size reported next to accuracy | Cost omission | Slack |
| W16 | Every figure traceable to its source table | Untraceable figures | Slack |
| W17 | Submitted to FYP InfoNet by 11:59 pm, 25 Sep 2026 | Schedule risk (R14) | CP |
| W18 | At least one substantive review per reporting period | Schedule risk (R14) | Slack |
| W19 | Draft circulated to supervisor before submission | Schedule risk (R14) | CP |
| W20 | Presented alongside the Progress Report period | Schedule risk (R14) | CP |
| W21 | Any triggered re-run completes without moving fixed milestones | Audit findings | Slack |
| W22 | All figures and tables verified before inclusion | Schedule risk (R14) | CP |
| W23 | Supervisor comments closed before submission | Schedule risk (R14) | CP |
| W24 | Ready before Semester B Week 10 | Schedule risk (R14) | Slack |
| W25 | Dry run completed before Semester B Week 11 | Environment failure (R2) | Slack |
| W26 | Package reproduces the reported tables from the archived inputs | Storage pressure (R4) | Slack |
| W27 | Absorbs slippage without moving fixed milestones | All risks | Slack |
| W28 | Abstract uploaded within the announced Semester B Week 8 window | Schedule risk (R14) | Slack |
| W29 | Poster delivered only if selected; no impact if not selected | Scope overload (R12) | Slack |

14.1  Critical path and slack

Remaining critical path (Semester A reporting period): W17 (this Planning Chart, due 25 Sep 2026) -> W18 (supervisor review) -> W19 (Progress Report) -> W20 (progress presentation, Nov 2026) -> W22 (Final Report drafting) -> W23 (revision and sign-off) -> M5 (Final Report submission, Semester B Week 12).

Scientific critical path already completed: W03 -> W06 (Gate) -> W07 -> W08 -> W09 (frozen selection) -> W11 (pre-Test freeze audit) -> W12 -> W13. This ordering is a hard design constraint: no Test/Holdout work was performed before frozen selection and the freeze audit.

Slack: W14 (secondary ILITOTAL / PTE-PIE analysis), W15 (resource comparison), W16 (figures), W24 (presentation), W25 (demonstration) and W26 (archive) have schedule slack of roughly two to six weeks and can absorb review delay. W21 and W27 are explicit buffer and iteration capacity; they are consumed first if an audit triggers re-work.

15.  Conclusion

This project is a reproducibility and evaluation study, not a claim that one model family is universally better. Its contribution is a complete, auditable comparison: one dataset and chronological split, one seven-variable input/output contract, train-only scaling, four horizons, ten frozen seeds, two deterministic references, six ablations and negative controls, a pre-execution checkpoint Gate, and a frozen selection rule that was never modified after the results were seen.

Two evidence phases are now complete and are reported separately. Wave-1 validation accepted 580 of 580 experimental rows and selected GPT-2 MIFlu as the validation winner (average_MSE_4L = 0.771), with NLinear the best Non-LLM model and overall runner-up (1.070). The subsequent one-time, isolated Test/Holdout evaluation of the frozen three-model comparison set completed 84 of 84 runs with a 25/25 terminal audit, and within that set NLinear obtained the lowest average_MSE_4L (2.739) ahead of GPT-2 MIFlu (3.051) and Seasonal-Naive (4.279).

The conclusion drawn is deliberately bounded. Within the evaluated setting, the Wave-1 validation advantage of the LLM champion did not survive distribution shift onto the COVID-era holdout, and both learned models remained substantially better than the zero-parameter seasonal reference. The result does not establish that NLinear defeats all eight architectures on Test, because only three frozen models were evaluated there, and it does not establish universal Non-LLM superiority.

Remaining work is the reporting and assessment stream: the Progress Report and progress presentation in Semester A Week 12, then the Final Report, final presentation, demonstration and reproducibility archive in Semester B Weeks 10-12. Success is defined as completing a correct, fair, reproducible and independently auditable comparison, and that definition is already met by the completed evidence phases.

16.  References

1. J. Moon, J. Shim, E. Kim and E. Hwang, “MIFlu: Large Language Model-Based Multimodal Influenza Forecasting Scheme,” IEEE Journal of Biomedical and Health Informatics, vol. 29, no. 10, pp. 7790-7801, Oct. 2025, doi: 10.1109/JBHI.2025.3561214.

2. A. Zeng, M. Chen, L. Zhang and Q. Xu, “Are Transformers Effective for Time Series Forecasting?” in Proceedings of the AAAI Conference on Artificial Intelligence (AAAI), vol. 37, no. 9, pp. 11121-11128, 2023, doi: 10.1609/aaai.v37i9.26317.

3. Y. Nie, N. H. Nguyen, P. Sinthong and J. Kalagnanam, “A Time Series is Worth 64 Words: Long-Term Forecasting with Transformers,” in International Conference on Learning Representations (ICLR), 2023. arXiv:2211.14730.

4. Y. Liu, T. Hu, H. Zhang, H. Wu, S. Wang, L. Ma and M. Long, “iTransformer: Inverted Transformers Are Effective for Time Series Forecasting,” in International Conference on Learning Representations (ICLR), 2024. arXiv:2310.06625.

5. M. Jin, S. Wang, L. Ma, Z. Chu, J. Y. Zhang, X. Shi, P.-Y. Chen, Y. Liang, Y.-F. Li, S. Pan and Q. Wen, “Time-LLM: Time Series Forecasting by Reprogramming Large Language Models,” in International Conference on Learning Representations (ICLR), 2024. arXiv:2310.01728.

6. P. Liu, H. Guo, T. Dai, N. Li, J. Bao, X. Ren, Y. Jiang and S.-T. Xia, “CALF: Aligning LLMs for Time Series Forecasting via Cross-modal Fine-Tuning,” in Proceedings of the AAAI Conference on Artificial Intelligence (AAAI), vol. 39, no. 18, pp. 18915-18923, 2025, doi: 10.1609/aaai.v39i18.34082.

7. C. Liu, Q. Xu, H. Miao, S. Yang, L. Zhang, C. Long, Z. Li and R. Zhao, “TimeCMA: Towards LLM-Empowered Multivariate Time Series Forecasting via Cross-Modality Alignment,” in AAAI Conference on Artificial Intelligence (AAAI), 2025 (Oral, Main Technical Track). arXiv:2406.01638.

8. S. C. Kramer and J. Shaman, “Development and validation of influenza forecasting for 64 temperate and tropical countries,” PLOS Computational Biology, vol. 15, no. 2, e1006742, 2019, doi: 10.1371/journal.pcbi.1006742. Source of the peak-timing (1 week) and peak-intensity (25%) hit conventions used in the secondary PTE/PIE analysis.

9. U.S. Centers for Disease Control and Prevention, “FluView / ILINet weekly influenza-like-illness surveillance (national),” retrieved through the CMU Delphi Epidata API (fluview endpoint); 1,025 weekly time points, seven variables. https://cmu-delphi.github.io/delphi-epidata/api/fluview.html. Raw snapshot retrieved 15 July 2026 (local copy last updated 18 July 2026).